## Project Status Dashboard
Project Status |  | Completed |  | 5% |  | Outstanding Issues
Ongoing Activities |  |  | Project Plan |  | Click on the gantt chart to see it in detail
Activity | % done
Top 5 Issues/Risks
0
0
Burndown Chart |  |  |  |  | Project Timeline
Report prepared by Victor Lopez | [6 empty] | 2014-09-09
Project Status Dashboard
Projecto : Nissan Certification Label

## Data
Enter Project Status |  | Enter the Project Milestone Data Here |  |  |  | Top 5 Issues/Risks
Overall Project Status | Amber | ID | Date | Milestone if any | Height | Issue/Risk
Overall Project Progress | 5% | 1 | 2014-09-20 09:00 | Analisis | 1
|  | 2 | 2014-10-01 03:00 | Diseño | 3
|  | 3 | 2014-10-14 06:00 | Codificacion / Pruebas | 1
|  | 4 | 2014-10-19 06:00 | Produccion | 2
|  | 5 | 2014-10-20 06:00 | Gold Support | 3
|  | 6 |  |  | 3
|  | 7 |  |  | 3
|  | 8 |  |  | 3
|  | 9 |  |  | 3
|  | 10 |  |  | 3
|  | 11 |  |  | 3
|  | 12 |  |  | 3
|  | 13 |  |  | 3
|  | 14 |  |  | 3
|  | 15 |  |  | 3
|  | 16 |  |  | 3
|  | 17 |  |  | 3
|  | 18 |  |  | 3
|  | 19 |  |  | 3
|  | 20 |  |  | 3
|  | 21 |  |  | 3
|  | 22 |  |  | 3
|  | 23 |  |  | 3
|  | 24 |  |  | 3
|  | 25 |  |  | 3
|  | 26 |  |  | 3
|  | 27 |  |  | 3
|  | 28 |  |  | 3
|  | 29 |  |  | 3
|  | 30 |  |  | 3
|  | 31 |  |  | 3
|  | 32 |  |  | 3
|  | 33 |  |  | 3
|  | 34 |  |  | 3
|  | 35 |  |  | 3
|  | 36 |  |  | 3
|  | 37 |  |  | 3
|  | 38 |  |  | 3
|  | 39 |  |  | 3
|  | 40 |  |  | 3
Enter dates & Milestones here

## Gantt Chart
[13 empty] | 41890 | 41891 | 41892 | 41893 | 41894 | 41897 | 41898 | 41899 | 41900 | 41901 | 41904 | 41905 | 41906 | 41907 | 41908 | 41911 | 41912 | 41913 | 41914 | 41915 | 41918 | 41919 | 41920 | 41921 | 41922 | 41925 | 41926 | 41927 | 41928 | 41929 | 41932 | 41933 | 41934 | 41935 | 41936 | 41939 | 41940 | 41941 | 41942 | 41943 | 41946 | 41947 | 41948 | 41949 | 41950 | 41953 | 41954 | 41955 | 41956 | 41957 | 41960 | 41961 | 41962 | 41963 | 41964 | 41967 | 41968 | 41969 | 41970 | 41971 | 41974 | 41975 | 41976 | 41977 | 41978 | 41981 | 41982 | 41983 | 41984 | 41985
[13 empty] | 41890: 2014-09-08; 41897: 2014-09-15; 41904: 2014-09-22; 41911: 2014-09-29; 41918: 2014-10-06; 41925: 2014-10-13; 41932: 2014-10-20; 41939: 2014-10-27; 41946: 2014-11-03; 41953: 2014-11-10; 41960: 2014-11-17; 41967: 2014-11-24; 41974: 2014-12-01; 41981: 2014-12-08 | Plan |  | Actual |  | Overlap
ID | Activity | Resource | Plan Start | Plan Duration | Actual Start | Actual Duration | % Done | ID | Activity | Plan Start | % Done |  | 41890: 2014-09-08; 41897: 2014-09-15; 41904: 2014-09-22; 41911: 2014-09-29; 41918: 2014-10-06; 41925: 2014-10-13; 41932: 2014-10-20; 41939: 2014-10-27; 41946: 2014-11-03; 41953: 2014-11-10; 41960: 2014-11-17; 41967: 2014-11-24; 41974: 2014-12-01; 41981: 2014-12-08 | Start | End | Start | End | Start | End
1 | Analisis |  | 2014-09-10 |  |  |  |  | 23 | Creación del Cliente de Testing para NX-Auto | 2014-10-01 15:00 | 0% | 0 | [70 empty] | 2014-10-01 15:00 | 2014-10-01 | 0 | 0 | 2014-09-07 | 2014-09-07
2 | Overview de la APP | Resource 1 | 2014-09-10 | 0.125 |  |  |  | 24 | Creación de Consumo de Excel - Lectura | 2014-10-02 03:00 | 0% | 0 | [70 empty] | 2014-10-02 03:00 | 2014-10-02 | 0 | 0 | 2014-09-07 | 2014-09-07
3 | configuración de Ambiente | Resource 1 | 2014-09-10 03:00 | 0.625 |  |  |  | 25 | Creación de Base de Datos Embebida | 2014-10-02 21:00 | 0% | 0 | [70 empty] | 2014-10-02 21:00 | 2014-10-02 | 0 | 0 | 2014-09-07 | 2014-09-07
4 | Definir los flujos existentes | Resource 1 | 2014-09-10 18:00 | 0.25 |  |  |  | 26 | Migracion Modulo Online | 2014-10-03 12:00 | 0% | 0 | [70 empty] | 2014-10-03 12:00 | 2014-10-06 | 0 | 0 | 2014-09-07 | 2014-09-07
5 | Comunicación NX-Auto Serial/TCP-ip | Resource 1 | 2014-09-11 | 0.75 |  |  |  | 27 | Migración del Modulo de Impresión | 2014-10-04 12:00 | 0% | 0 | [70 empty] | 2014-10-04 12:00 | 2014-10-04 | 0 | 0 | 2014-09-07 | 2014-09-07
6 | Consumo del Excel Modelos de Autos | Resource 1 | 2014-09-11 18:00 | 0.125 |  |  |  | 28 | Migracion y Desarrollo Modulo Modelos | 2014-10-06 06:00 | 0% | 0 | [70 empty] | 2014-10-06 06:00 | 2014-10-07 | 0 | 0 | 2014-09-07 | 2014-09-07
7 | Conexión a la Impresora | Resource 1 | 2014-09-11 21:00 | 1.25 |  |  |  | 29 | Migracion Modulo Enviar Logo | 2014-10-07 06:00 | 0% | 0 | [70 empty] | 2014-10-07 06:00 | 2014-10-07 | 0 | 0 | 2014-09-07 | 2014-09-07
8 | Investigación de Compatibilidad versiones .NET vs Impresora | Resource 1 | 2014-09-13 03:00 | 0.75 |  |  |  | 30 | Migracion Modulo Inicializacion | 2014-10-07 18:00 | 0% | 0 | [70 empty] | 2014-10-07 18:00 | 2014-10-07 | 0 | 0 | 2014-09-07 | 2014-09-07
9 | Creación de Plantillas para la impresora | Resource 1 | 2014-09-14 21:00 | 3 |  |  |  | 31 | Modulo de Creacion de Etiquetas | 2014-10-08 06:00 | 0% | 0 | [70 empty] | 2014-10-08 06:00 | 2014-10-10 | 0 | 0 | 2014-09-07 | 2014-09-07
10 | Documentar Casos de Uso en base a los flujos Existentes | Resource 1 | 2014-09-17 21:00 | 1.25 |  |  |  | 32 | Test de Regresion | 2014-10-10 06:00 | 0% | 0 | [70 empty] | 2014-10-10 06:00 | 2014-10-13 | 0 | 0 | 2014-09-07 | 2014-09-07
11 | Documentación de Impresiones en Plantillas | Resource 1 | 2014-09-19 03:00 | 1 |  |  |  | 33 | Bug Fixing | 2014-10-11 06:00 | 0% | 0 | [70 empty] | 2014-10-11 06:00 | 2014-10-14 | 0 | 0 | 2014-09-07 | 2014-09-07
12 | Compendio de Documentación | Resource 1 | 2014-09-20 03:00 | 0.25 |  |  |  | 34 | QA y Validacion | 2014-10-14 06:00 | 0% | 0 | [70 empty] | 2014-10-14 06:00 | 2014-10-14 | 0 | 0 | 2014-09-07 | 2014-09-07
13 | Diseño |  | 2014-09-20 09:00 |  |  |  |  | 35 | QA | 2014-10-14 06:00 | 0% | 0 | [70 empty] | 2014-10-14 06:00 | 2014-10-17 | 0 | 0 | 2014-09-07 | 2014-09-07
14 | Diseño Módulo de Conexión NX-Auto | Resource 1 | 2014-09-20 09:00 | 0.75 |  |  |  | 36 | UAT | 2014-10-17 06:00 | 0% | 0 | [70 empty] | 2014-10-17 06:00 | 2014-10-21 | 0 | 0 | 2014-09-07 | 2014-09-07
15 | Diseño de Módulo de Consumo De Excel | Resource 1 | 2014-09-22 03:00 | 0.5 |  |  |  | 37 | Production | 2014-10-19 06:00 | 0% | 0 | [70 empty] | 2014-10-19 06:00 | 2014-10-20 | 0 | 0 | 2014-09-07 | 2014-09-07
16 | Diseño de Arquitectura MVC | Resource 1 | 2014-09-22 15:00 | 1 |  |  |  | 38 | Gold Support | 2014-10-20 06:00 | 0% | 0 | [70 empty] | 2014-10-20 06:00 | 2014-11-07 | 0 | 0 | 2014-09-07 | 2014-09-07
17 | Diseño de Base de Datos Embebida | Resource 1 | 2014-09-23 15:00 | 1.25 |  |  |  | 39 | 0 | 2014-11-03 06:00 | 0% | 0 | [70 empty] | 2014-11-03 06:00 | 2014-11-03 | 0 | 0 | 2014-09-07 | 2014-09-07
18 | Diseño del Modulo de Creación de Etiquetas | Resource 1 | 2014-09-24 21:00 | 2 |  |  |  | 40 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
19 | Diseño de Componentes | Resource 1 | 2014-09-26 21:00 | 1.25 |  |  |  | 41 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
20 | Documentación de Diseño | Resource 1 | 2014-09-29 03:00 | 2 |  |  |  | 42 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
21 | Codificacion / Pruebas |  | 2014-10-01 03:00 |  |  |  |  | 43 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
22 | Creación del Modulo de conexión NX-Auto | Resource 1 | 2014-10-01 03:00 | 0.5 |  |  |  | 44 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
23 | Creación del Cliente de Testing para NX-Auto | Resource 1 | 2014-10-01 15:00 | 0.5 |  |  |  | 45 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
24 | Creación de Consumo de Excel - Lectura | Resource 1 | 2014-10-02 03:00 | 0.75 |  |  |  | 46 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
25 | Creación de Base de Datos Embebida | Resource 1 | 2014-10-02 21:00 | 0.625 |  |  |  | 47 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
26 | Migracion Modulo Online | Resource 1 | 2014-10-03 12:00 | 1 |  |  |  | 48 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
27 | Migración del Modulo de Impresión | Resource 1 | 2014-10-04 12:00 | 0.75 |  |  |  | 49 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
28 | Migracion y Desarrollo Modulo Modelos | Resource 1 | 2014-10-06 06:00 | 1 |  |  |  | 50 | 0 | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
29 | Migracion Modulo Enviar Logo | Resource 1 | 2014-10-07 06:00 | 0.5 |  |  |  | 51 |  | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
30 | Migracion Modulo Inicializacion | Resource 1 | 2014-10-07 18:00 | 0.5 |  |  |  | 52 |  | 0 | 0% | 0 | [70 empty] | 0 | 0 | 0 | 0 | 0 | 0
31 | Modulo de Creacion de Etiquetas | Resource 1 | 2014-10-08 06:00 | 2
32 | Test de Regresion | Resource 1 | 2014-10-10 06:00 | 1
33 | Bug Fixing | Resource 1 | 2014-10-11 06:00 | 2
34 | QA y Validacion |  | 2014-10-14 06:00
35 | QA | Resource 1 | 2014-10-14 06:00 | 3
36 | UAT | Resource 1 | 2014-10-17 06:00 | 2
37 | Production |  | 2014-10-19 06:00 | 1
38 | Gold Support |  | 2014-10-20 06:00 | 14
39 |  |  | 2014-11-03 06:00
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Note on F4: Duration in working days (excluding weekends and holidays)
Note on H4: Duration in working days (excluding weekends and holidays)
Show Gantt for:
Gantt Chart
Project Plan Data

## Burndown Chart
Burn down chart | [11 empty] | Don't edit this table
Deliverable Burn Down | [5 empty] | Budget Burn Down | [5 empty] | Selected Chart |  | 2
| Burned down |  | Balance |  | Weekly Completed |  | Burned down |  | Balance |  | Weekly Completed |  | Burned down |  | Balance |  | Weekly Completed
Week | Planned | Actual | Planned | Actual |  | Week | Planned | Actual | Planned | Actual |  | Week | Planned | Actual | Planned | Actual
0 |  |  |  |  | #N/A | 0 |  |  |  |  | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A
1 |  |  | 0 | #N/A | #N/A | 1 |  |  | 0 | #N/A | #N/A | 1 | 0 | 0 | 0 | #N/A | #N/A
2 |  |  | 0 | #N/A | #N/A | 2 |  |  | 0 | #N/A | #N/A | 2 | 0 | 0 | 0 | #N/A | #N/A
3 |  |  | 0 | #N/A | #N/A | 3 |  |  | 0 | #N/A | #N/A | 3 | 0 | 0 | 0 | #N/A | #N/A
4 |  |  | 0 | #N/A | #N/A | 4 |  |  | 0 | #N/A | #N/A | 4 | 0 | 0 | 0 | #N/A | #N/A
5 |  |  | 0 | #N/A | #N/A | 5 |  |  | 0 | #N/A | #N/A | 5 | 0 | 0 | 0 | #N/A | #N/A
6 |  |  | 0 | #N/A | #N/A | 6 |  |  | 0 | #N/A | #N/A | 6 | 0 | 0 | 0 | #N/A | #N/A
7 |  |  | 0 | #N/A | #N/A | 7 |  |  | 0 | #N/A | #N/A | 7 | 0 | 0 | 0 | #N/A | #N/A
8 |  |  | 0 | #N/A | #N/A | 8 |  |  | 0 | #N/A | #N/A | 8 | 0 | 0 | 0 | #N/A | #N/A
9 |  |  | 0 | #N/A | #N/A | 9 |  |  | 0 | #N/A | #N/A | 9 | 0 | 0 | 0 | #N/A | #N/A
10 |  |  | 0 | #N/A | #N/A | 10 |  |  | 0 | #N/A | #N/A | 10 | 0 | 0 | 0 | #N/A | #N/A
11 |  |  | 0 | #N/A | #N/A | 11 |  |  | 0 | #N/A | #N/A | 11 | 0 | 0 | 0 | #N/A | #N/A
12 |  |  | 0 | #N/A | #N/A | 12 |  |  | 0 | #N/A | #N/A | 12 | 0 | 0 | 0 | #N/A | #N/A
13 |  |  | 0 | #N/A | #N/A | 13 |  |  | 0 | #N/A | #N/A | 13 | 0 | 0 | 0 | #N/A | #N/A
14 |  |  | 0 | #N/A | #N/A | 14 |  |  | 0 | #N/A | #N/A | 14 | 0 | 0 | 0 | #N/A | #N/A
15 |  |  | 0 | #N/A | #N/A | 15 |  |  | 0 | #N/A | #N/A | 15 | 0 | 0 | 0 | #N/A | #N/A
16 |  |  | 0 | #N/A | #N/A | 16 |  |  | 0 | #N/A | #N/A | 16 | 0 | 0 | 0 | #N/A | #N/A
17 |  |  | 0 | #N/A | #N/A | 17 |  |  | 0 | #N/A | #N/A | 17 | 0 | 0 | 0 | #N/A | #N/A
18 |  |  | 0 | #N/A | #N/A | 18 |  |  | 0 | #N/A | #N/A | 18 | 0 | 0 | 0 | #N/A | #N/A
19 |  |  | 0 | #N/A | #N/A | 19 |  |  | 0 | #N/A | #N/A | 19 | 0 | 0 | 0 | #N/A | #N/A
20 |  |  | 0 | #N/A | #N/A | 20 |  |  | 0 | #N/A | #N/A | 20 | 0 | 0 | 0 | #N/A | #N/A
Enter data in these cells

## Issue Tracker
Issue Tracker Template
Date
# | Issue | Priority | Open | Close | Comments
1 | Delays to set the targets and metircs by resource | Low | 2014-06-10 |  | Comments goes here
2
3
4
5
6
7
8
9
10

## Agreements
Agreements
# | Item | Date | Comments
1 | Record any agreement on the project here | 2014-06-10 | Comments
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## Calculations
All the dashboard calculations are here
No. of ongoing Activities This week | 0 | The list of ongoing activities is automatically populated based on Project Plan. Overwrite values in the grayed portion to see your own list.
# | List of ongoing activities |  | List of ongoing Activities (cleaned) | Completion % | Total |  | Open Issue Summary |  |  | BurnDown Chart Types
1 | 0 | 1 |  |  | 100% |  | High | 0 |  | Budget
2 | 0 | 2 |  |  | 100% |  | Medium | 0 |  | Deliverable
3 | 0 | 3 |  |  | 100% |  | Low | 1
4 | 0 | 4 |  |  | 100%
5 | 0 | 5 |  |  | 100%
Today Details | Y
#N/A | 4
Calculations for Gantt Chart Do not modify this sheet
Gantt Start | 2014-09-10 |  | Plan | 1 |  | Show Plan | TRUE |  | Show Help? | FALSE
Weekday | 4 |  | Actual | 2 |  | Show Actual | FALSE |  | Gantt chart prepared on 15,Nov 2012. Showing activities 1 to 30 in dates 12 Mar '12 to 15 Jun '12
Start Monday | 2014-09-08 |  | Both | 3 |  | show Both | FALSE
Offset | 0
Offset Start | 2014-09-08 |  |  |  |  | 41889
Activity Offset | 22 |  | Display Option | 1 |  | Plan Start
[11 empty] | Chosen | Overlap
# | ID | Activity | Plan Start | Plan Duration | Actual Start | Actual Duration | % Done | Plan End | Actual End |  | Start | Start | End
1 | 23 | Creación del Cliente de Testing para NX-Auto | 2014-10-01 15:00 | 0.5 | 0 | 0 | 0% | 2014-10-01 | 0 |  | 2014-10-01 15:00 | 2014-09-07 | 2014-09-07
2 | 24 | Creación de Consumo de Excel - Lectura | 2014-10-02 03:00 | 0.75 | 0 | 0 | 0% | 2014-10-02 | 0 |  | 2014-10-02 03:00 | 2014-09-07 | 2014-09-07
3 | 25 | Creación de Base de Datos Embebida | 2014-10-02 21:00 | 0.625 | 0 | 0 | 0% | 2014-10-02 | 0 |  | 2014-10-02 21:00 | 2014-09-07 | 2014-09-07
4 | 26 | Migracion Modulo Online | 2014-10-03 12:00 | 1 | 0 | 0 | 0% | 2014-10-06 | 0 |  | 2014-10-03 12:00 | 2014-09-07 | 2014-09-07
5 | 27 | Migración del Modulo de Impresión | 2014-10-04 12:00 | 0.75 | 0 | 0 | 0% | 2014-10-04 | 0 |  | 2014-10-04 12:00 | 2014-09-07 | 2014-09-07
6 | 28 | Migracion y Desarrollo Modulo Modelos | 2014-10-06 06:00 | 1 | 0 | 0 | 0% | 2014-10-07 | 0 |  | 2014-10-06 06:00 | 2014-09-07 | 2014-09-07
7 | 29 | Migracion Modulo Enviar Logo | 2014-10-07 06:00 | 0.5 | 0 | 0 | 0% | 2014-10-07 | 0 |  | 2014-10-07 06:00 | 2014-09-07 | 2014-09-07
8 | 30 | Migracion Modulo Inicializacion | 2014-10-07 18:00 | 0.5 | 0 | 0 | 0% | 2014-10-07 | 0 |  | 2014-10-07 18:00 | 2014-09-07 | 2014-09-07
9 | 31 | Modulo de Creacion de Etiquetas | 2014-10-08 06:00 | 2 | 0 | 0 | 0% | 2014-10-10 | 0 |  | 2014-10-08 06:00 | 2014-09-07 | 2014-09-07
10 | 32 | Test de Regresion | 2014-10-10 06:00 | 1 | 0 | 0 | 0% | 2014-10-13 | 0 |  | 2014-10-10 06:00 | 2014-09-07 | 2014-09-07
11 | 33 | Bug Fixing | 2014-10-11 06:00 | 2 | 0 | 0 | 0% | 2014-10-14 | 0 |  | 2014-10-11 06:00 | 2014-09-07 | 2014-09-07
12 | 34 | QA y Validacion | 2014-10-14 06:00 | 0 | 0 | 0 | 0% | 2014-10-14 | 0 |  | 2014-10-14 06:00 | 2014-09-07 | 2014-09-07
13 | 35 | QA | 2014-10-14 06:00 | 3 | 0 | 0 | 0% | 2014-10-17 | 0 |  | 2014-10-14 06:00 | 2014-09-07 | 2014-09-07
14 | 36 | UAT | 2014-10-17 06:00 | 2 | 0 | 0 | 0% | 2014-10-21 | 0 |  | 2014-10-17 06:00 | 2014-09-07 | 2014-09-07
15 | 37 | Production | 2014-10-19 06:00 | 1 | 0 | 0 | 0% | 2014-10-20 | 0 |  | 2014-10-19 06:00 | 2014-09-07 | 2014-09-07
16 | 38 | Gold Support | 2014-10-20 06:00 | 14 | 0 | 0 | 0% | 2014-11-07 | 0 |  | 2014-10-20 06:00 | 2014-09-07 | 2014-09-07
17 | 39 | 0 | 2014-11-03 06:00 | 0 | 0 | 0 | 0% | 2014-11-03 | 0 |  | 2014-11-03 06:00 | 2014-09-07 | 2014-09-07
18 | 40 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
19 | 41 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
20 | 42 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
21 | 43 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
22 | 44 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
23 | 45 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
24 | 46 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
25 | 47 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
26 | 48 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
27 | 49 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
28 | 50 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
29 | 51 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
30 | 52 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
Formulas:
List of ongoing activities = MIN(tblPlan[Plan Start],tblPlan[Actual Start])
List of ongoing activities = C54+[List of ongoing activities, row above]*7
List of ongoing Activities (cleaned) = INDEX(tblPlan[Plan Start],[List of ongoing activities])
Total = INDEX(tblPlan[Actual Start],[List of ongoing activities])
Plan End = WORKDAY([List of ongoing Activities (cleaned)],[Completion %])
Actual End = WORKDAY([Total],[Actual Duration])
Start = CHOOSE(F57,[List of ongoing Activities (cleaned)],[Total],[Total])
Start = IF(OR([Plan End]<[Total],[Actual End]<[List of ongoing Activities (cleaned)]),dummyDate,MAX([List of ongoing Activities (cleaned)],[Total]))
End = IF(OR([Plan End]<[Total],[Actual End]<[List of ongoing Activities (cleaned)]),dummyDate,MIN([Plan End]:[Actual End]))
Note on E5: Change this to see new activities in dashboard

## Sheet1
Tarea | Inicio | Fin
Analisis | 2014-09-10 | 2014-09-20 09:00
Diseño | 2014-09-20 09:00 | 2014-10-01 03:00
Codigo/Pruebas | 2014-10-01 03:00 | 2014-10-14 06:00
QA / UAT | 2014-10-14 06:00 | 2014-10-19 06:00
Produccion | 2014-10-19 06:00 | 2014-10-20 06:00
Gold Support | 2014-10-20 06:00 | 2014-11-03 06:00
Formulas:
Inicio = +[Fin, row above]